# General

## Definitions

    - Person-Day: One person for eight hours within regular Contractor working hours.

## Submittals

    - Informational Submittals:

Training Schedule: Submit not less than 15 working days prior to start of equipment installation and revise as necessary for acceptance.

Lesson Plan: Submit proposed lesson plan not less than 15 working days prior to scheduled training and revise as necessary for acceptance.

## Qualification of manufacturer’s representative

    - Authorized representative of the manufacturer, factory trained, and experienced in the technical applications, installation, operation, and maintenance of respective equipment, subsystem, or system, with full authority by the equipment manufacturer to issue the certifications required of the manufacturer. Additional qualifications may be specified in individual specification sections.

    - Representative subject to acceptance by Owner and Consultant. No substitute representatives will be allowed unless prior written approval by Owner and Consultant has been given.

# Products – Not used

# Execution

## Fulfillment of specified minimum services

    - Furnish manufacturer’s services when required by an individual specification section, to meet the requirements of this Section.

    - Where time is necessary in excess of that stated in the Specifications for manufacturers’ services, or when a minimum time is not specified, the time required to perform the specified services shall be considered incidental.

    - Schedule manufacturer’s services to avoid conflict with other onsite testing or other manufacturers’ onsite services.

    - Determine, before scheduling services, that all conditions necessary to allow successful testing have been met.

    - Only those days of service approved by Consultant will be credited to fulfill the specified minimum services.

    - When specified in individual specification sections, manufacturer’s onsite services shall include:

- Assistance during product (system, subsystem, or component) installation to include observation, guidance, instruction of Contractor’s assembly, erection, installation or application procedures.

Inspection, checking, and adjustment as required for product (system, subsystem, or component) to function as warranted by manufacturer and necessary to furnish Manufacturer’s Certificate of Proper Installation.

Providing copies of all manufacturer’s representatives field notes and data to Consultant daily.

Revisiting the site as required to correct problems and until installation and operation are acceptable to Consultant.

Resolution of assembly or installation problems attributable to, or associated with, respective manufacturer’s products and systems.

Assistance during functional and performance testing, and facility startup and evaluation.

Training of Owner’s personnel in the operation and maintenance of respective product as required.

Additional requirements may be specified elsewhere.

## Manufacturer’s certificate of compliance

    - When specified in individual Specification section, submit certificate of compliance prior to shipment of product or material.

    - Consultant may permit use of certain materials or assemblies prior to sampling and testing if accompanied by accepted certification of compliance.

    - Certificate of compliance shall be signed by product manufacturer certifying that product or material specified conforms to or exceeds specification. Attach supporting reference data, affidavits, and certifications as appropriate.

## Manufacturer’s certificate of proper installation

    - When so specified, a Manufacturer’s Certificate of Proper Installation form, a copy of which is attached to this section, shall be completed and signed by the equipment manufacturer's representative.

    - Such form shall certify that the signing party is a duly authorized representative of the manufacturer, is empowered by the manufacturer to inspect, approve, and operate their equipment and is authorized to make recommendations required to assure that the equipment is complete and operational.

## Training

    - General:

- Coordinate training, be present during training coordination meetings with Owner, and be familiar with operation and maintenance manual information specified in Section 01 78 23 – Operation and Maintenance Data.

Furnish manufacturer’s representatives for detailed classroom and hands-on training to Owner’s personnel on operation and maintenance of specified product (system, subsystem, component) and as may be required in applicable Specifications.

Manufacturer’s representative shall be familiar with facility operation and maintenance requirements as well as with specified equipment.

Furnish complete training materials, to include operation and maintenance data, to be retained by each trainee.

Complete training at least ten working days prior to beginning of facility startup.

    - Training Schedule:

- List specified equipment and systems that require training services and show:

Respective manufacturer.

Estimated dates for installation completion.

Estimated training dates.

Allow for two sessions to cover several shifts as required.

Adjust schedule to ensure training of appropriate personnel as deemed necessary by Owner, and to allow full participation by manufacturer’s representatives. Adjust schedule for interruptions in operability of equipment.

Coordinate with Section 01 32 16 – Construction Progress  Schedule, 01 31 13 – Project Co-ordination, 01 32 13 – Scheduling of Work, and Section 01 91 00 – Commissioning.

    - Lesson Plan: When manufacturer or vendor training of Owner personnel is specified, prepare for each required course, a lesson plan containing but not limited to the following information:

- Title and objectives.

Recommended types of attendees (e.g., managers, engineers, operators, maintenance).

Course description and outline of course content.

Format (e.g., lecture, self-study, demonstration, hands-on).

Instruction materials and equipment requirements.

Resumes of instructors providing the training.

## Supplements

    - The supplement provided below, following “End of section”, forms part of this Specification.

- Forms: Manufacturer’s Certificate of Proper Installation.

End of section

Manufacturer’s certificate of proper installation

| Owner: | Equipment/system: |
| --- | --- |
| Equipment tag number: | Equipment serial number: |
| Contract: D20XX-XXX | Specification Section: |
| I hereby certify that the above-referenced equipment/system has been: (Check Applicable) Installed in accordance with Manufacturer’s recommendations. Inspected, checked, and adjusted. Serviced with proper initial lubricants. Electrical and mechanical connections meet quality and safety standards. All applicable safety equipment has been properly installed. Functionally tested. System has been performance tested and meets or exceeds specified performance requirements. (When complete system of one manufacturer) Note: Attach any performance test documentation from manufacturer. |  |
| Comments: |  |
| I, the undersigned Manufacturer’s Representative, hereby certify that I am (i) a duly authorized representative of the manufacturer, (ii) empowered by the manufacturer to inspect, approve, and operate their equipment and (iii) authorized to make recommendations required to assure that the equipment furnished by the manufacturer is complete and operational, except as may be otherwise indicated herein. I further certify that all information contained herein is true and accurate. |  |
| Date: , 20___ |  |
| Manufacturer: Manufacturer’s Authorized Representative: (Authorized Signature) |  |